NOVA  RL

Final Execution Roadmap

Team BytePair  ·  Aryan Verma & Aadyaa Soni

Meta PyTorch · OpenEnv Hackathon

Deadline: 8 April 2026, 11:59 PM IST

| 9 Days Build Window | 5 Checks Auto-validation | 2 Builders Clear ownership |
| --- | --- | --- |

01  —  THE BIG PICTURE

What Are We Building?

We're not building an AI model. We're building the world the AI lives in.

Think of it like Chess We build the board, the rules, and the scoring system. The judges bring their AI player. Our job: make a board that tests the player well.

Concretely — we're building an ETL data quality environment. The AI agent gets a batch of messy data, decides how to clean it, and we score how well it did.

Three difficulty levels. Three tasks. One clean environment.

02  —  THE 5 CHECKS THAT MATTER

Pass All 5 or Go Home

These are automated. No partial credit. No exceptions.

| # | Check | What it actually means |
| --- | --- | --- |
| 1 | HF Space deploys | Your app URL must respond. reset() must return 200 OK. If this fails, nothing else matters. |
| 2 | OpenEnv spec passes | openenv.yaml is valid. step(), reset(), state() all work. Typed models in place. |
| 3 | Dockerfile builds | docker build runs clean. Container starts without errors. |
| 4 | inference.py finishes | Script runs all 3 tasks, prints scores, completes in under 20 minutes. |
| 5 | 3 tasks with graders | Easy, Medium, Hard all run. Each grader returns a score between 0.0 and 1.0. |

Hard Constraints from the Hackathon vCPU = 2 ¦ RAM = 8 GB ¦ inference.py must finish under 20 minutes No Ollama. No heavy models. Keep everything lightweight.

03  —  PROJECT STRUCTURE

Every File, One Job

Flat, clean, no surprises. Each file does exactly one thing.

NOVA_RL/ ├── app.py → HF startup + server wiring ├── Dockerfile → Container setup ├── inference.py → Baseline evaluation script (MANDATORY: root level) ├── openenv.yaml → Environment registration (MANDATORY) ├── requirements.txt → Dependencies ├── README.md → Docs for judges ├── .env.example → API_BASE_URL, MODEL_NAME, HF_TOKEN └── nova_rl_env/ ├── __init__.py → Package entry ├── environment.py → reset() / step() / state() ├── models.py → Observation, Action, Reward types ├── rewards.py → Scoring logic ├── tasks.py → Easy / Medium / Hard definitions ├── datagen.py → Synthetic dirty data generator └── graders.py → Task scoring (always 0.0 to 1.0)

04  —  WHO OWNS WHAT

Clear Ownership. No Overlap.

Every file has exactly one owner. If it's not listed under your name, don't touch it.

Aryan

app.py Aryan HF startup entrypoint. Wires the environment to the server. Business logic stays out of here.

Dockerfile Aryan Python base image. Install dependencies. Copy project. Clean startup command. Port 7860.

inference.py Aryan Runs all 3 tasks, fixed seeds, prints scores. OpenAI-compatible client. Must finish under 20 min.

openenv.yaml Aryan Environment name, entrypoint class, task list (easy/medium/hard), minimal metadata.

requirements.txt Aryan Only what's needed. Lightweight. Works locally, in Docker, and on HF Spaces.

nova_rl_env/__init__.py Aryan Tiny. Clean package imports. Export the main environment class.

nova_rl_env/environment.py Aryan The heart. reset() builds fresh state. state() exposes current state. step(action) runs one turn and returns observation + reward.

nova_rl_env/models.py Aryan Typed Observation, Action, Reward Pydantic models. Fields must match what environment, inference, and graders all expect.

nova_rl_env/rewards.py Aryan Reward shaping. Partial credit for progress. Penalties for unsafe promotion or over-quarantine. Always deterministic.

Aadyaa

README.md Aadyaa Project overview, environment description, observation/action space, task objectives, setup instructions, baseline scores.

nova_rl_env/tasks.py Aadyaa Easy, Medium, Hard task definitions. Clear objectives. Difficulty increases meaningfully across levels.

nova_rl_env/datagen.py Aadyaa Generates synthetic messy ETL data. Task-specific anomalies. Fixed seeds. Lightweight output.

nova_rl_env/graders.py Aadyaa Scores task completion 0.0 to 1.0. No randomness. No LLM calls. Same input always gives same score.

Integration Contract (define this on Day 1) environment.py imports from graders.py using this exact signature: grade(task_id: str, state: dict, action: Action) -> float Aadyaa writes graders.py to match this. Aryan calls it from step(). No surprises at merge.

05  —  THE 3 TASKS

Easy → Medium → Hard

Judges run all three. Each one tests the AI agent on harder problems.

| Level | What the AI must fix | Anomaly types active | Scoring |
| --- | --- | --- | --- |
| Easy | Fix null fields and obvious duplicates | null_field, duplicate_key (10% anomaly rate) | Promotion rate → 0.0 to 1.0 |
| Medium | Fix type errors and date format violations | Adds type_mismatch, malformed_date (20%) | Weighted: promotion + quarantine penalty |
| Hard | Handle schema drift and correlated multi-column faults | All fault types + schema_drift_prob = 0.1 (30%) | Full R_system: α×promotion − β×quarantine − γ×latency |

06  —  HOW JUDGES SCORE US

What Matters, and How Much

| Criteria | Weight | Our status |
| --- | --- | --- |
| Real-world utility — Does this solve a problem humans actually have? | 30% | Strong — ETL data quality is a real, painful problem |
| Task & grader quality — Are tasks well-designed? Graders fair? | 25% | Strong — 3 levels, deterministic graders |
| Environment design — Clean state, sensible episodes, good reward signal? | 20% | Good — reward per step, not just end-of-episode |
| Code quality & spec compliance — Does openenv validate pass? | 15% | Covered — if we follow this roadmap |
| Creativity & novelty — Something fresh? | 10% | Good — ETL env hasn't appeared in OpenEnv before |

07  —  DAY BY DAY

9 Days. Ship It.

Deadline: 8 April, 11:59 PM IST. Start counting from 1 April.

| Day | Aryan | Aadyaa |
| --- | --- | --- |
| Day 1 | openenv init → models.py → rewards.py skeleton. Share grader contract with Aadyaa. | datagen.py — synthetic batches with all anomaly types. Fixed seeds. |
| Day 2 | environment.py — reset() and state() working. app.py wired to server. | tasks.py — easy, medium, hard configs. Plug into datagen. |
| Day 3 | environment.py — step() working end-to-end. LLM call in inference with timeout + fallback. | graders.py — all 3 graders. Return 0.0–1.0. Deterministic. |
| Day 4 | rewards.py — partial progress signal, penalties. Reward per step, not just at end. | Full local test: datagen → environment → graders all connected. |
| Day 5 | inference.py — 3 fixed-seed episodes. Scores print clean. | requirements.txt finalized. openenv validate passes locally. |
| Day 6 | openenv.yaml + Dockerfile. Local docker build clean. | README.md — env description, spaces, setup, baseline scores. |
| Day 7 | Deploy to HF Spaces. Ping /reset manually. Confirm 200 OK. | Run pre-validation script from hackathon. Fix any issues. |
| Day 8 | Run full submission check. Fix anything. SUBMIT. | Cross-check checklist. Support Aryan on final submission. |
| Day 9 (buffer) | If needed: bug fixes, re-deploy, re-submit. | If needed: docs polish, cross-check scores. |

08  —  RULES TO NOT FORGET

Non-negotiables

LLM Usage

- Only inference.py calls the LLM via OpenAI-compatible client

- Read API_BASE_URL, MODEL_NAME, HF_TOKEN from os.getenv() — never hardcode

- Add a 5-second timeout + rule-based fallback so the run never hangs

Memory & Performance

- sentence-transformers: use all-MiniLM-L6-v2 only (384-dim, lightweight)

- ChromaDB: in-memory mode only on HF Spaces — not persistent

- Pre-download the model in Dockerfile so cold start doesn't eat your 20 minutes

- Target under 15 minutes for inference.py to leave buffer

Submission

- inference.py must be in the ROOT directory — not inside nova_rl_env/

- Only Aryan (team lead) submits the final HF Spaces URL

- Run the hackathon's pre-validation script before submitting

- Deadline: 8 April 11:59 PM IST — confirm in Discord if you see the 7 April mention anywhere

09  —  FINAL CHECKLIST

Before You Hit Submit

Run through this the night before. Every box must be checked.

|  | Check |
| --- | --- |
| [ ] | openenv validate passes locally |
| [ ] | docker build runs without errors |
| [ ] | inference.py completes in under 15 minutes locally |
| [ ] | HF Space URL responds — curl -X POST <url>/reset returns 200 |
| [ ] | All 3 graders return scores between 0.0 and 1.0 |
| [ ] | openenv.yaml has name, entry_point, tasks list, metadata |
| [ ] | API_BASE_URL, MODEL_NAME, HF_TOKEN set as HF Secrets (not hardcoded) |
| [ ] | inference.py is in the root directory (not inside any subfolder) |
| [ ] | Hackathon pre-validation script runs clean |
| [ ] | README covers: environment, observation/action space, task descriptions, setup, baseline scores |
| [ ] | Deadline confirmed: 8 April 11:59 PM IST |

Build the board. Ship the environment. Let the LLM play. Nova RL · Team BytePair · April 2026